## Slide 1: Transforming Education: Establishing a Digital Library
Dire Dawa Comprehensive Secondary School
Presented by Arif Yusuf Bakar
December 3, 2024

## Slide 2: Background and Context
Attended Dire Dawa Comprehensive Secondary High School (9th & 10th grades).
Lived as a refugee in Kenya before immigrating to the U.S.
Founder and principal of Bultum Academy, Minnesota.
Committed to giving back by bridging the digital divide in Ethiopian schools.

## Slide 3: Needs Assessment
• School has over 3,000 students on two shifts.
• Existing resources:
18 i2/i3-based computers in one room.
33 i2/i3-based computers in another room.
• Limited IT infrastructure and no digital library system.
There is no G-Suite and website
• Identified need for modern digital learning solutions, G-Suite, and a Website.

## Slide 4: Digital Library Setup
Key Components:
Server with large storage capacity.
Router, switch, and Wi-Fi access points.
Devices (laptops, tablets, Chromebooks).
Open-source library software (e.g., DSpace, Greenstone).
Educational Content:
eBooks, videos, and interactive learning modules.

## Slide 5: Installation and Training
Site Preparation:
- Ensure power and physical space for equipment.
Technical Installation:
- Set up server, router, and Wi-Fi.
- Configure devices and load educational content.
Training:
- IT teachers: Managing and maintaining the library.
- Students: Effective usage of the library.

## Slide 6: G-Suite for Education
G-Suite for Education:
- The school currently lacks access to G-Suite for Education, a free platform provided by Google.
- This suite includes essential tools like Google Classroom, Google Docs, Sheets, and Drive to facilitate modern teaching and learning.
- Plan: Collaborate with Google to secure full access to G-Suite for Education, empowering teachers and students with digital tools.

## Slide 7: Website Development
Website Development:
- Plan to develop a dedicated website for the school to enhance its digital presence and communication.
- Timeline: The website is targeted for completion and launch by January/February 2025.
- Features: Information portal for students, parents, and teachers, event updates, and a platform for showcasing achievements.

## Slide 8: Official Launch Ceremony
Event Highlights:
- Invite stakeholders: officials, community leaders, students.
- Showcase the digital library in action.
- Emphasize its impact on empowering students.
Outcome:
- Inspire support for ongoing sustainability.

## Slide 9: Post-Launch Follow-Up
Monitoring and Support:
- Feedback mechanism for students and staff.
- Regular visits or virtual check-ins.
Sustainability:
- Partner with local NGOs and government bodies.
- Ensure resources are updated and operational.

## Slide 10: Timeline and Milestones
• Needs Assessment: Early December 2024.
• Procurement and Shipping: Mid to end of December 2024
• Installation and Training: End of December 2024? Or Beginning of January 2025
• Launch Ceremony: Beginning to Mid January 2025.